# New Zealand Disability Strategy Implementation – 5 Year Roadmap – March 2026

This table gives a high-level schedule and status of the work against the 34 actions in the New Zealand Disability Strategy 2026-2030. The status column shows progress on actions as at March 2026. Some actions are not started but will be started during the year.

## Legend for the year columns:

- S = This work is being scoped

- D = This work is in design/development

- I = This work is being implemented.

Colour coding of cells in the year columns show the latest stage of the action for that year. For example, if in one year the action is being designed and implemented the cell will be shaded green for implemented. If in one year the action is being scoped and designed the cell will be shaded blue for designed.

| Action Number | Action Name | Agencies involved | Status | 2026 | 2027 | 2028 | 2029 | 2030 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Education 1 | Put $266 million into early intervention services, so children’s learning support needs are identified earlier, and families don’t have to wait as long for support. | Lead: Ministry of Education Support: Various NGOs, alternate providers | Underway (since 2025) | I | tbc | tbc | tbc | tbc |
| Education 2 | Look at new ways to provide targeted and specialist learning support, including working with private providers and community organisations to reduce wait times. | Lead: Ministry of Education Support: Various NGOs, alternate providers | Underway | S, D, I | tbc | tbc | tbc | tbc |
| Education 3 | Improve the learning support system so it is easier for educators, families and learners to use by: - funding a Learning Support Coordinator for all schools with learners in Years 1-8 - making application processes for learning support easier. | Lead: Ministry of Education | Underway (part completed) | I | I | I | I | tbc |
| Education 4 | Invest funding into more specialist school satellite classrooms to provide choice for parents. | Lead: Ministry of Education | Underway | S, D, I | I | I | tbc | tbc |
| Education 5 | Work with the Ministry of Disabled People – Whaikaha to develop improvements in teacher training that support teachers to meet the needs of disabled students. | Lead: Ministry of Education Support: Whaikaha | Underway (initial scoping) | S, D | D | I | tbc | tbc |
| Education 6 | Work with the Ministry of Disabled People - Whaikaha to look for ways to improve accountability for schools and school boards by reporting on learning and achievement outcomes of all disabled learners. | Lead: Ministry of Education Support: Whaikaha, Stats NZ | Underway (finalizing decision) | D, I | tbc | tbc | tbc | tbc |
| Education 7 | Use existing funding to support Kaupapa Māori settings to access tools, knowledge and skills so they can meet the needs of their disabled ākonga (students) with high quality programmes. | Lead: Ministry of Education Support: tbc | Underway (ongoing) | I | I | I | I | I |
| Education 8 | Work with the Ministry of Disabled People - Whaikaha to look for ways to identify disabled learners in education data so their needs and progress are better understood. | Lead: Ministry of Education Support: Whaikaha | Not yet started | S | tbc | tbc | tbc | tbc |
| Education 9 | The Tertiary Education Commission (TEC) will continue monitoring provider progress on implementing their Disability Action Plans. The TEC will consult with disabled student representative groups including the National Disabled Students’ Association on how this function is implemented. | Lead: Tertiary Education Commission Support: Ministry of Education | Underway (ongoing) | I | I | I | I | I |
| Employment 1 | Put information and guidance that helps disabled people to identify and match their skills and interests with job pathways in one place and make it accessible. This should include guidance for disabled people leaving school or education. | Lead: Whaikaha (scoping phase only) Leads for subsequent phases tbc | Not yet started | n/a | S | tbc | tbc | tbc |
| Employment 2 | Review specialist employment supports, consulting with disabled people, to improve employment outcomes. | Lead: Ministry of Social Development Support: Whaikaha | Underway | D, I | I | I | tbc | tbc |
| Employment 3 | Work with disabled people, employers and employer networks to create mentor programmes – so disabled people can get career support from disabled professionals or employers. | Lead: Whaikaha Support: NZ Disability Employers’ Network, Business NZ | Not yet started | S, D, I (pilot) | I (full) | tbc | tbc | tbc |
| Employment 4 | Work with disabled people and support providers to create a repository of resources. The resources will include knowledge, success stories and practical information – helping employers and employer networks support disabled people. | Lead: Whaikaha Support: NZ Disability Employers’ Network, All Is For All | Underway (near completion) | I (web-site) | tbc | tbc | tbc | tbc |
| Employment 5 | Work with disabled people, their whānau and supporters, employers and employer networks, to promote and enable the design of jobs and workplaces for disabled people. This means: inclusion of disabled people; flexible working arrangements and reasonable accommodations; and assessing workplace accessibility. Government agencies should lead by example in the employment of disabled people. | Lead: Whaikaha Support: Public Service Commission | Underway | S | tbc | tbc | tbc | tbc |
| Employment 6 | Create an awareness campaign for employers and employees. The campaign will include guidance on accessibility and inclusion, data and reports, and will highlight the positive impact of disabled people on workplaces. | Lead: Whaikaha Support: NZ Disability Employers’ Network, All Is For All | Underway | D, I | I | em-bedd-ing | tbc | tbc |
| Health 1 | Review and improve policies and practices, so the health journey is equitable, accessible, and inclusive. This review will cover all interactions with the health system: communication, information, technology, decision-making, service design and delivery, and the built environment. Self-determination will be key, including making sure tools for self-determination and supported decision making are standard practice in healthcare – especially for people with different communication, cognitive or psychosocial needs. | Lead: Health New Zealand Support: Ministry of Health, Whaikaha | Underway (relevant work underway through the NZ Health Plan, further scoping of priorities for future reviews underway) | D (NZ Health Plan), S (NZDS priorit-ies) | tbc | tbc | tbc | tbc |
| Health 2 | Train the health workforce to deliver services that are inclusive, culturally safe, and easy to navigate. This includes: Increasing disabled people throughout the health and disability workforce. This can be done through recruitment and workplace policies, inclusive and accessible work environments, and career development. And: Embedding disability responsiveness and lived experience in workforce training and ongoing professional development. | Lead: Health New Zealand Support: Whaikaha, Ministry of Health (tbc – only in case of any legislative scope components), Education, Health and Community Industry Skills Board (via Tertiary Education Commission) - tbc | Underway (relevant work underway through the NZ Health Plan, further scoping of NZDS priorities planned) | I (NZ Health Plan), S (NZDS priorit-ies) | tbc | tbc | tbc | tbc |
| Health 3 | Build disabled people’s skills and knowledge to take up health system roles. Government agencies will find ways to build disabled people’s capability for health system design, consultation, monitoring, leadership, and advisory and governance roles. | Potential co-leads: Ministry of Health and Health New Zealand - tbc following scoping Support: Education, Health and Community Industry Skills Board (via Tertiary Education Commission) – tbc, Whaikaha | Not yet started | S | tbc | tbc | tbc | tbc |
| Health 4 | Identify disabled people in national health data. This will make disabled people more visible in the health system, so population health outcomes can be monitored better, while ensuring information security, privacy and protection. | Leads: Ministry of Health (policy phase); Health New Zealand (implementation phase) Support: Whaikaha, Stats NZ - tbc | Underway (scoping completed, development of fundamental policy in 2026) | D | tbc | tbc | tbc | tbc |
| Health 5 | Put a system in place so disabled people can record their accessibility needs against their National Health Index (NHI) number. Recording people’s accessibility needs will mean those needs can be easily shared with health providers. Disabled people will not have to repeat their needs to providers, and providers will be better able to meet those needs. This work will be guided by disability community expectations and data sovereignty. | Lead: Health New Zealand Support: Ministry of Health, Whaikaha, Stats NZ - tbc | Underway (BC development for PPNHI is underway); scoping of NZDS priorities in 2026 | S, D | tbc | tbc | tbc | tbc |
| Housing 1 | Develop, consult on and promote clear definitions of accessible homes. These will describe key features of different levels of accessibility (for example, from basic universal design through to fully accessible). Clear definitions of accessible homes can support the development of voluntary guidelines for accessibility for residential dwellings (housing action 6). | Lead: Whaikaha Support: Ministry of Business, Innovation and Employment, Ministry of Housing and Urban Development, Kāinga Ora | Not yet started | S, D | I | tbc | tbc | tbc |
| Housing 2 | Improve data matching between disabled people and social housing properties with appropriate accessible features that meet their needs. This will help ensure disabled people and their whānau are prioritised to accessible properties. Data matching will identify disabled people’s housing needs and social housing that meets those needs. This is particularly important for those with high and/or complex needs. Data collected could inform future investment in the supply of social housing. | Lead: Ministry of Social Development Support: Ministry of Health, Whaikaha, Ministry of Housing and Urban Development, Kāinga Ora | Underway (initial scoping) | S | tbc | tbc | tbc | tbc |
| Housing 3 | Identify any barriers to increasing supply of affordable, accessible houses in the private market and investigate how these barriers could be removed. Understanding barriers to the supply of accessible housing will help target potential interventions to improve supply. | Lead: Ministry of Housing and Urban Development Support: Ministry of Business, Innovation and Employment, Whaikaha | Not yet started | S | D | D | Report | tbc |
| Housing 4 | Review the housing modification system and look at ways to improve it. Making the housing modification system more efficient could reduce current problems: inaccessibility of homes, increased costs and health and safety issues for disabled people, whānau and carers. | Lead: MSD (Disability Support Services) Support: Whaikaha, Kāinga Ora – tbc, Oranga Tamariki tbc, ACC tbc | Underway | D, I | tbc | tbc | tbc | tbc |
| Housing 5 | Collect and publish annual data on disabled people’s housing needs, to compare with the housing being built in each region. This could help encourage the housing market to produce more accessible housing. This will help to fill the gap in data on accessible housing and raise the profile of the demand for accessible homes. Data can also be used to measure progress in increasing the supply of accessible housing. | Lead: Whaikaha Support: Ministry of Housing and Urban Development, Ministry of Business, Innovation and Employment, Disability Support Services | Not yet started | S | tbc | tbc | tbc | tbc |
| Housing 6 | Develop voluntary national guidelines on accessibility for residential dwellings. Guidelines would be based on the definitions for accessible homes in housing action 1 and would set out best practice guidance for how to build accessible homes. | Lead: Ministry of Business Innovation and Employment Support: Whaikaha, Ministry of Housing and Urban Development, Kāinga Ora | Not yet started | n/a | n/a | S | tbc | tbc |
| Housing 7 | Review the social housing system, including considering the diverse needs of disabled people and how these could be addressed. | Leads: Ministry of Social Development, and Ministry of Housing and Urban Development Support: Whaikaha | Underway (initial scoping) | S | tbc | tbc | tbc | tbc |
| Justice 1 | Implement a safeguarding framework for disabled people in long-term detention settings (such as prisons and youth justice residences) and Disability Support Services funded residential facilities. The framework will include preventing, reporting, responding, and safely removing disabled people from abusive situations. | Lead: tbc following scoping Support: Department of Corrections, Oranga Tamariki, Disability Support Services, Whaikaha, Police | Not yet started | S | tbc | tbc | tbc | tbc |
| Justice 2 | Carry out a cross-agency project to fix gaps in information about disabled people’s experiences of crime. This will include disabled people in residential and secure facilities, and issues like cyberbullying. | Lead: tbc following scoping Support: Whaikaha, Disability Support Services, Department of Corrections, Ministry of Justice, Police | Not yet started | n/a | S | tbc | tbc | tbc |
| Justice 3 | Develop a social investment plan for early intervention and support, to reduce disabled children and young people entering the youth justice system. | Lead: tbc following scoping Support: Oranga Tamariki, Disability Support Services, Whaikaha | Not yet started | S | tbc | tbc | tbc | tbc |
| Justice 4 | The Law Commission has been asked to review the Criminal Procedure (Mentally Impaired Persons) Act 2003 (CPMIP). This review is expected to look at the interface of the CPMIP with other relevant legislation, such as the Intellectual Disability (Compulsory Care and Rehabilitation) Act 2003 and Mental Health (Compulsory Assessment and Treatment) Act 1992. | Lead: Ministry of Justice Support: Whaikaha | Underway (Law commission scoping review) | S | tbc | tbc | tbc | tbc |
| Justice 5 | Review, as work programmes allow, protections for disabled people in family law, including adoption, guardianship and personal property rights. Reviews will consider where stronger provisions or support are needed, supported decision-making, and using plain language in key justice sector legislation and processes. Reviewing human rights legislation, including whether additional protections against discrimination are needed, should also be considered as work programmes allow. | Lead: Ministry of Justice Support: Whaikaha | Underway (awaiting report from Law Commission) | S | tbc | tbc | tbc | tbc |
| Justice 6 | Weave understanding from safeguarding approaches for disabled people into the multi-agency responses to family violence. This includes training the workforce to make sure disabled people experiencing violence and abuse receive a safe, coordinated response centered on their needs. | Lead: Centre for Family Violence & Sexual Violence Prevention Support: Whaikaha, Disability Support Services, Other agencies involved in the Centre’s multi-agency work programme | Not yet started | S, D | tbc | tbc | tbc | tbc |
| Justice 7 | Create a plan to train the justice sector workforce so it is more disability competent, including Deaf cultural competence and using mana and trauma informed practices. This plan will increase disabled people in the workforce and consider mandatory professional standards. | Lead: tbc following scoping Support: Police, Department of Corrections, Ministry of Justice, Oranga Tamariki, Whaikaha | Underway | S | tbc | tbc | tbc | tbc |